Guide 2. APT Development Project

Final Subject

1. Project APT Progress Summary

Below, you'll find various fields that you'll need to complete with the requested information.

| APT project progress summary | During this phase, we have made significant progress in the development of the APT Project. We completed the structuring of the database, the design of the entity-relationship model, and the initial implementation of the backend with Django. In addition, we established the connection with PostgreSQL to store and manage historical data on Chilean fruit exports. The specific objectives related to data collection, cleaning, and normalization have been achieved, as well as the preliminary design of the predictive model for export prices. We also made progress in defining the variables that influence the prediction. |
| --- | --- |
| Objetivos | (Optional if adjusted) |
| Methodology | (Optional if adjusted) |
| Evidence of progress | The main pieces of evidence of progress are: - Database design implemented in PostgreSQL. - Functional backend prototype developed in Django. - Linkl git - First predictive model trained with historical data to estimate export prices. These pieces of evidence demonstrate the technical progress of the project and support the fulfillment of the initial objectives. To ensure the quality of the work, cross-validation methodologies have been used to evaluate the predictive model, and the entire process has been documented on GitHub, ensuring traceability and technical consistency. Additional evidence: Evidence |
| 2. Monitoring of the Work Plan |
| Carefully examine your work plan, focusing especially on the progress and adjustments column. |

| Work Plan |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Competence or Unit of Competence | Activities | Resources | Duration of the activity | Responsible | Observations | Progress status | Ajustes |
| Requirements gathering | Analysis of data sources | PC, internet | 2 weeks | Complete equipment | We decided to build the database using only ODEPA data. Some requirements were defined thanks to the interview. | Completed |  |
| Data modeling | BD Design | PostgreSQL | 2 weeks | Miguel / Jesús | All ODEPA columns were included to build the database. | Completed |  |
| Software development | Backend in Django | Python/Django | 3 weeks | Miguel / Jeús | Started with an initial prototype. | In progress | Due week 9 |
| Software development | Frontend in React | React.js | 3 weeks | Jesús | - | Not started |  |
| AI/Data Analytics | ML Training | Python, scikit-learn | 3 weeks | Vicente | First iteration of models started: Prophet and RF. LSTM will be implemented next. | In progress |  |
| Validation | Usability testing | Surveys, prototype | 2 weeks | Complete equipment | A Minimum Viable Product (MVP) is required. | Not started |  |
| Closing | Report and presentation | Word, PPT | 2 weeks | Complete equipment | Requires completion of previous stages. | Not started |  |

3. Adjustments Based on Monitoring

Dig deeper into your work plan observations. Analyze the planned activities and identify what aspects facilitated or hindered the plan's execution. Discuss how you addressed and/or will address the obstacles. Finally, highlight any adjustments you made to the work plan based on this analysis.

Factors that have facilitated and/or hindered the development of the work plan: During the development of the APT project, we encountered several factors that both facilitated and hindered the execution of the work plan. At the beginning, it was challenging to determine where to start and how to organize ourselves, as there was still some uncertainty about the project’s functions and structure. To solve this, we updated the Gantt chart tasks and followed the phases we defined, which helped us to start — the most important step — and move forward in an organized manner. We also faced difficulties coordinating as a team, especially when integrating everyone’s work. We solved this by properly configuring the GitHub repository and maintaining constant communication through meetings and messages. Other obstacles included inconsistencies in the CSV data and the large volume of information we were handling. To overcome this, we conducted a thorough data review before loading it into the database, ensuring everything was correct for the predictive model. We also decided to work with a smaller amount of data. Among the factors that facilitated progress, the clear division of roles stood out: Jesús Martínez is in charge of the frontend, Miguel Muñoz of the backend, and Vicente Valenzuela of the predictive model. This allowed parallel work and faster progress.

Adjusted or removed activities: Some adjustments were made to the work plan mainly to optimize time and focus efforts on the most important project functions. For example, the user system and login development were completely discarded, since authentication and registration are not necessary for this version. Instead, we decided to prioritize core functionalities such as data visualization, simulation, and prediction. Additionally, in the data loading stage, we opted to work with a smaller portion of the dataset, as the original set covers around 20 years of information, which increased processing time and complexity. We decided to use a representative sample from the most recent years to maintain good response times and facilitate testing. Currently, we are also considering reducing the amount of data per year in the final version to optimize system performance and focus the analysis on more recent periods, which are the most relevant for the predictive model.

Activities not started or delayed: So far, the main project activities have been initiated and are in various stages of progress, such as the development of the frontend, backend, and predictive model. However, one of the activities that could be considered delayed is the greater involvement of the interviewee, since the interview was only recently conducted during the project’s development. As a result, the obtained information has not yet had a significant impact on the project. To prevent this delay from affecting overall development, a second meeting with the interviewee was scheduled to explore technical aspects and validate the system’s functionalities. Additionally, the schedule will be adjusted to integrate their input into the following stages, especially during the refinement of requirements and the final validation.

En caso de que el Proyecto APT sea grupal, en esta columna deben indicar el nombre de los responsables de cada tarea o actividad. Esto posteriormente permitirá diferenciar la evaluación por cada integrante.